## Read me
Taskiem QA tracker: 2 to 27 November 2026
ISPEND DIGITAL SERVICES LTD · Confidential · Goes with the QA test plan
How to use it
Fill in | Only the shaded (light green-grey) columns. Everything else is filled in already or counts itself.
Test cases | One row per case, already in the order of the plan, with its planned day. Filter by Day to see today's cases. Fill in Result, Date run, Device and browser, Bug IDs and Notes.
Bugs | One row per bug. Row 4 is an example: copy its style, then delete it before your first weekly report. IDs go BUG-001, BUG-002… and are never reused.
Daily log | One row per day, already dated. The case counts fill themselves from the Test cases tab; you fill in the rest by 17:30.
Exploratory | The five planned sessions with their charters. Fill in what you did and found.
Accounts | Your test identities and organisations. Never write a password here.
Summary | Counts that fill themselves: results by area and by day, bugs by severity and status, and the KPIs. Copy these into your weekly report.
Result words | Pass · Pass with note · Fail · Blocked · Not run (choose from the list in the cell)
Severity | S1 Critical: money, data or trust at risk; message the engineering lead within 1 hour · S2 Major: a feature does not work, no way round · S3 Minor: works badly or with a way round · S4 Small: wording, looks, suggestions
Bug status | New · Confirmed · Needs info · In progress · Fixed: ready to retest · Closed · Reopened · Won't fix · Duplicate · Not a bug
R | R in the Regression column marks the 66 cases run before every release.
Rules | Test data only. Never a real customer's details, a real card number or a live payment key. Never a password in this file.

## Summary
Summary
Fills itself from the other tabs. Copy into the weekly report.
Results by area | Cases | Pass | Pass with note | Fail | Blocked | Not run | No result yet | % with a result
Smoke test | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0%
Core platform | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 0%
Chat (Telegram) | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 0%
Reconciliation: invoices, payments and money | 95 | 0 | 0 | 0 | 0 | 0 | 95 | 0%
Storefronts, orders, bookings, forms and agents | 76 | 0 | 0 | 0 | 0 | 0 | 76 | 0%
Schools | 96 | 0 | 0 | 0 | 0 | 0 | 96 | 0%
Across the product | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 0%
All | 379 | 0 | 0 | 0 | 0 | 0 | 379 | 0%
Bugs by severity | Logged | Open | Fixed: ready to retest | Closed | Reopened | Won't fix, duplicate, not a bug | Needs info
S1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
S4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
All | 0 | 0 | 0 | 0 | 0 | 0 | 0
"Open" means not Closed and not Won't fix, Duplicate or Not a bug. The example row (row 4 of Bugs) is not counted.
KPI (plan section 9) | Target | Now
Cases with a result | 100% | 0%
Cases Not run | 2% | 0%
Bugs reproduced without asking (never Needs info) | 90%
Bugs not closed as Duplicate or Not a bug | 90%
S1 bugs messaged within 1 hour | 100%
Fixed bugs retested within 1 working day | 95%
Daily logs done by 17:30 | 100%
Exploring sessions logged (of 5) | 5 | 0
Targets come from the QA test plan, section 9. Blank means nothing to measure yet.
Results by planned day | Date | Planned | With a result | Pass | Fail | Blocked | Not run | % with a result
Day 1 | 2026-11-02 | 8 | 0 | 0 | 0 | 0 | 0 | 0%
Day 2 | 2026-11-03 | 18 | 0 | 0 | 0 | 0 | 0 | 0%
Day 3 | 2026-11-04 | 17 | 0 | 0 | 0 | 0 | 0 | 0%
Day 4 | 2026-11-05 | 16 | 0 | 0 | 0 | 0 | 0 | 0%
Day 5 | 2026-11-06 | 19 | 0 | 0 | 0 | 0 | 0 | 0%
Day 6 | 2026-11-09 | 26 | 0 | 0 | 0 | 0 | 0 | 0%
Day 7 | 2026-11-10 | 26 | 0 | 0 | 0 | 0 | 0 | 0%
Day 8 | 2026-11-11 | 26 | 0 | 0 | 0 | 0 | 0 | 0%
Day 9 | 2026-11-12 | 21 | 0 | 0 | 0 | 0 | 0 | 0%
Day 10 | 2026-11-13 | 16 | 0 | 0 | 0 | 0 | 0 | 0%
Day 11 | 2026-11-16 | 19 | 0 | 0 | 0 | 0 | 0 | 0%
Day 12 | 2026-11-17 | 25 | 0 | 0 | 0 | 0 | 0 | 0%
Day 13 | 2026-11-18 | 18 | 0 | 0 | 0 | 0 | 0 | 0%
Day 14 | 2026-11-19 | 14 | 0 | 0 | 0 | 0 | 0 | 0%
Day 15 | 2026-11-20 | 7 | 0 | 0 | 0 | 0 | 0 | 0%
Day 16 | 2026-11-23 | 25 | 0 | 0 | 0 | 0 | 0 | 0%
Day 17 | 2026-11-24 | 26 | 0 | 0 | 0 | 0 | 0 | 0%
Day 18 | 2026-11-25 | 22 | 0 | 0 | 0 | 0 | 0 | 0%
Day 19 | 2026-11-26 | 23 | 0 | 0 | 0 | 0 | 0 | 0%
Day 20 | 2026-11-27 | 7 | 0 | 0 | 0 | 0 | 0 | 0%

## Test cases
ID | Area | Feature | What to do | Expected result | Needs | Day | Planned date | Regression | Result | Date run | Device and browser | Bug IDs | Notes
SM-01 | Smoke test | Smoke | Open the staging address on a laptop and on your phone | The sign-in page loads on both, in Taskiem's look, with no error |  | 1 | 2026-11-02 | R
SM-02 | Smoke test | Smoke | Sign in with the test owner account | You land on the dashboard; your organisation's name shows |  | 1 | 2026-11-02 | R
SM-03 | Smoke test | Smoke | Open every item in the menu once | Each page opens; nothing is blank or shows a technical error |  | 1 | 2026-11-02
SM-04 | Smoke test | Smoke | Run the workflow "Remind me every day" from its template, once | The run completes and the reminder arrives on Telegram | Telegram | 1 | 2026-11-02 | R
SM-05 | Smoke test | Smoke | Open the operator console (/ops) | Storefront reviews, Reports and Field agents show | Operator account | 1 | 2026-11-02
SM-06 | Smoke test | Smoke | Create a data table with one column and add one row | The table and row are saved |  | 1 | 2026-11-02
SM-07 | Smoke test | Smoke | Send "help" to the Taskiem bot on Telegram | The bot answers with what you can do, starting with your organisation's name in brackets | Telegram | 1 | 2026-11-02 | R
SM-08 | Smoke test | Smoke | Sign out, then try to open the dashboard address directly | You are sent to the sign-in page |  | 1 | 2026-11-02
CP-01 | Core platform | Sign-up | On the sign-in page choose "Create an account"; fill in organisation, your name, a new email and a 12+ character password | You are signed in at once and land on Get started | Email | 2 | 2026-11-03 | R
CP-02 | Core platform | Sign-up | Try to sign up with a password of 11 characters; then with the password equal to the email | Both refused with a plain message |  | 2 | 2026-11-03
CP-03 | Core platform | Sign-up | Try to sign up with an email that already has an account | Refused: the email is already in use |  | 2 | 2026-11-03
CP-04 | Core platform | Sign-up | Try a throwaway mailbox address (for example a mailinator.com address) and a name containing a web link | Both refused |  | 2 | 2026-11-03
CP-05 | Core platform | Sign-up | Make 6 sign-ups from the same network in one day | The sixth is refused (limit of 5 a day per address, unless engineering changed it) |  | 2 | 2026-11-03
CP-06 | Core platform | Email confirmation | Open the confirmation email and click the link | Email confirmed; the checklist ticks "Confirm your email" | Email | 2 | 2026-11-03 | R
CP-07 | Core platform | Email confirmation | Click the same confirmation link a second time; then use a link older than 24 hours if you have one | The used link does not work again; the old link is refused | Email | 2 | 2026-11-03
CP-08 | Core platform | Email confirmation | Before confirming, try to invite a member and to create an API key | Both refused with "confirm your email address first" |  | 2 | 2026-11-03
CP-09 | Core platform | Email confirmation | On Get started press "Send the link again" four times | Three are sent; the fourth asks you to wait (one every 20 minutes) | Email | 2 | 2026-11-03
CP-10 | Core platform | Get started | Work through the checklist: confirm email, link Telegram, pick a template, connect, publish, run once, invite a teammate | Each step ticks itself when done; the page shows the minutes from sign-up to first successful run |  | 2 | 2026-11-03 | R
CP-11 | Core platform | Get started | Time yourself from sign-up to the first successful run using the guided first workflow | Under 15 minutes. Record the time and what slowed you down |  | 2 | 2026-11-03
CP-12 | Core platform | Get started | Open the help panels on Get started, Templates, Connections and Settings | Each shows a few plain sentences; any "learn more" link opens a real page |  | 2 | 2026-11-03
CP-13 | Core platform | Sign-in | Sign in with a wrong password several times | Refused each time with a plain message; after many tries you are slowed down |  | 2 | 2026-11-03
CP-14 | Core platform | Password | Change your password under Account; sign out and in with the new one | Old password no longer works; new one does |  | 2 | 2026-11-03
CP-15 | Core platform | Password | Use "forgot password" (if offered) and follow the email link | You can set a new password; the link works once | Email | 2 | 2026-11-03
CP-16 | Core platform | Passkey | Under Account add a passkey (phone fingerprint or PIN); sign out; "Sign in with a passkey" | Signed in without a password | Phone | 2 | 2026-11-03
CP-17 | Core platform | Authenticator | Under Account set up an authenticator app (Google Authenticator or similar) and confirm a code | Enrolled. Five wrong codes in a row lock codes for 15 minutes | Phone | 2 | 2026-11-03
CP-18 | Core platform | Sessions | Sign in on laptop and phone; sign out on one | The other session still works until signed out; signed-out pages are not reachable with Back |  | 2 | 2026-11-03
CP-19 | Core platform | Members | Members & keys: invite a second email as Operator; accept the invitation from that mailbox | The person joins with the Operator role | Email, second person | 3 | 2026-11-04
CP-20 | Core platform | Members | Invite someone, then cancel the invitation before it is accepted | The link no longer works |  | 3 | 2026-11-04
CP-21 | Core platform | Roles | Signed in as a Viewer, try to edit a workflow, create a table and open Members | Not allowed: buttons hidden or a plain refusal, never a crash | Second person | 3 | 2026-11-04 | R
CP-22 | Core platform | Roles | As a Viewer, paste the address of an owner-only page (for example /settings/billing or a workflow's edit page) into the browser | Refused; no data shown | Second person | 3 | 2026-11-04 | R
CP-23 | Core platform | Custom roles | Create a custom role (for example Cashier) with two permissions; give it to a member | The member can do exactly those two things and nothing else |  | 3 | 2026-11-04
CP-24 | Core platform | Members | Remove a member; the removed person tries to sign in to the organisation | They no longer reach it |  | 3 | 2026-11-04
CP-25 | Core platform | Audit log | Open the audit log after the steps above | Every invite, role change, removal and sign-in change is listed with who and when |  | 3 | 2026-11-04
CP-26 | Core platform | Personal data | Open a table with phone numbers as a member without the reveal permission; then as owner press Show | Masked for the member (•••4567); shown for the owner, and the reveal appears in the audit log |  | 3 | 2026-11-04
CP-27 | Core platform | Templates | Open Templates; search for "reminder"; open three templates | Search finds them; each template page says what it does and what it needs in plain words |  | 3 | 2026-11-04
CP-28 | Core platform | Templates | Set up "Remind me every day" through the guided screen; publish; run once | Completes; the reminder arrives on Telegram | Telegram | 3 | 2026-11-04 | R
CP-29 | Core platform | Templates | Set up "Weekly SMS reminders from your debtors data table": let it make the debtors table; add two debtors with your own phone numbers; run it | Each debtor with a balance gets an SMS; the run lists each one | SMS | 3 | 2026-11-04
CP-30 | Core platform | Templates | Set up "Send an invoice and hear when it is paid" | Invoice is sent; when paid with a Paystack test card the owner hears | Paystack test, SMS or email | 3 | 2026-11-04
CP-31 | Core platform | Templates | Fill a template's details with mistakes: leave a required box empty, type letters in a time box | Each mistake is pointed out in plain words before saving |  | 3 | 2026-11-04
CP-32 | Core platform | Connections | Connections: connect Paystack with the TEST secret key | Accepted and checked; shown as test mode | Paystack test | 3 | 2026-11-04 | R
CP-33 | Core platform | Connections | Try to connect Paystack with a wrong key | Refused with a plain message; nothing saved |  | 3 | 2026-11-04
CP-34 | Core platform | Connections | Switch a connection off; try to publish a workflow that uses it | Publishing is refused, listing the connection as needed, with a Connect button |  | 3 | 2026-11-04 | R
CP-35 | Core platform | Readiness | Publish a workflow that writes to a table that does not exist | Refused; offered "Make it" with the right columns; after making it, publishing succeeds |  | 3 | 2026-11-04
CP-36 | Core platform | Builder | Workflows > New workflow; try each "When should it run?" card once | Each opens the builder with the right first card |  | 4 | 2026-11-05
CP-37 | Core platform | Builder | Build: On a schedule > send yourself a Telegram message (Tell me). Use + to add the step. Test workflow | Each step gets a green tick; nothing is actually sent during a test |  | 4 | 2026-11-05 | R
CP-38 | Core platform | Builder | Add an If with a Yes and an empty No; test with values that take each path | The path not taken is faded "Did not need to run" |  | 4 | 2026-11-05
CP-39 | Core platform | Builder | Add a value from an earlier step into a message using "/" or Add a field | The value appears in the message when the workflow runs |  | 4 | 2026-11-05
CP-40 | Core platform | Builder | Move cards, Tidy up, Undo and Redo, add a note, delete a step | Each works; deleting a step joins the steps around it |  | 4 | 2026-11-05
CP-41 | Core platform | Builder | Save draft; publish; Start run; open the Runs tab | A new version is saved; the run appears with each step's result |  | 4 | 2026-11-05 | R
CP-42 | Core platform | Builder | Open the same workflow in two browser tabs; change and save in both | The second save merges or shows the conflict to choose; nothing is lost silently |  | 4 | 2026-11-05
CP-43 | Core platform | Builder | Open the builder on your phone | Steps show as a list; a step's window opens full screen; Save draft and Publish work | Phone | 4 | 2026-11-05
CP-44 | Core platform | Builder | Try to publish a workflow with no steps | Refused with a plain message |  | 4 | 2026-11-05
CP-45 | Core platform | Plain words | Across the builder with Advanced OFF, look for technical words (JSON, schema, expression, cron, kobo, token, webhook, payload, API key) | None appear outside Details or Advanced. Log each one found |  | 4 | 2026-11-05
CP-46 | Core platform | Runs | Make a run fail on purpose (for example a message to an invalid phone number); open the run | The failed step is marked; the error is in plain words, technical detail under Details |  | 4 | 2026-11-05
CP-47 | Core platform | Runs | Use the run list filters (status, workflow); open a running run | Filters work; the live view updates as steps finish |  | 4 | 2026-11-05
CP-48 | Core platform | AI builder | Describe it: "every Friday at 10am text the customers in my debtors table who still owe me" | A draft is built, read back as plain numbered steps, and saved only after you confirm | AI key on staging | 4 | 2026-11-05
CP-49 | Core platform | AI builder | Ask it for something that moves money ("pay my staff every month end") | It drafts with an approval before any payment; it never publishes by itself | AI key on staging | 4 | 2026-11-05
CP-50 | Core platform | AI builder | Ask for nonsense, or something Taskiem cannot do | A polite answer, no broken draft |  | 4 | 2026-11-05
CP-51 | Core platform | AI repair | On a failed run, open the repair suggestion (if shown) | It explains the fix in plain words; accepting needs a normal publish | AI key on staging | 4 | 2026-11-05
CP-52 | Core platform | Tables | Tables > New table "debtors": name (text, required), phone (phone), balance (number), paid (yes/no) | Created (the first table can take a minute or two) |  | 5 | 2026-11-06 | R
CP-53 | Core platform | Tables | Add rows: a correct one; one with no name; one with letters in balance; one with a phone in local form 080… | Bad rows refused with the reason; the phone is stored as +234… |  | 5 | 2026-11-06 | R
CP-54 | Core platform | Tables | Import a CSV of 50 rows with 3 bad rows; export the table as CSV | Good rows in, bad rows reported with their line; export opens in Excel correctly | CSV file | 5 | 2026-11-06
CP-55 | Core platform | Tables | Add a column; drop a column; try to add a required column to a table that has rows | Add and drop work (drop asks to confirm); the required column is refused |  | 5 | 2026-11-06
CP-56 | Core platform | Tables | Delete a table used by a published workflow | You are warned or refused; nothing breaks silently |  | 5 | 2026-11-06
CP-57 | Core platform | Approvals | Workflow with an approval step for role Owner; start it; approve from the Approvals inbox | The run waits, then continues after approval |  | 5 | 2026-11-06 | R
CP-58 | Core platform | Approvals | Same, but reject | The run takes the rejected path or stops, as designed |  | 5 | 2026-11-06
CP-59 | Core platform | Approvals | Approval needing two people (four-eyes); the person who started it tries to approve | Self-approval refused; a second person can approve | Second person | 5 | 2026-11-06 | R
CP-60 | Core platform | Approvals | Approval policy with step-up (authenticator); approve | Asks for the authenticator code or passkey before accepting |  | 5 | 2026-11-06
CP-61 | Core platform | Approvals | Delegate your approval role to a colleague for 2 days | The colleague sees requests marked "covering for…"; ending the delegation stops it | Second person | 5 | 2026-11-06
CP-62 | Core platform | Approvals | Leave an approval past its timeout | It does what the step says on timeout (reject, fail or escalate) |  | 5 | 2026-11-06
CP-63 | Core platform | Settings | Secrets & settings: add a setting, a secret; use both in a workflow | Workflow reads them; the secret is never shown again in full |  | 5 | 2026-11-06
CP-64 | Core platform | Settings | Turn the Advanced switch on and off | Advanced shows step ids, Code and JSON tabs; off hides them |  | 5 | 2026-11-06
CP-65 | Core platform | Alerts | Settings > Alerts: a Telegram alert channel for failed runs; make a run fail | The alert arrives on Telegram | Telegram | 5 | 2026-11-06
CP-66 | Core platform | People you message | Settings > People you message: a customer opts in to Telegram updates via a form's thank-you page; then sends STOP | Updates arrive on Telegram, not SMS; after STOP they stop; Remove removes the person | Telegram, second Telegram account | 5 | 2026-11-06
CP-67 | Core platform | Email trigger | A workflow started by an email; send an email to its address | A run starts with the email's details | Mail domain on staging | 5 | 2026-11-06
CP-68 | Core platform | Phone app | On your phone, "Add to Home screen"; open Taskiem from the icon; approve something from Home | Opens like an app; approving works | Phone | 5 | 2026-11-06
CP-69 | Core platform | Languages | Switch the language (Pidgin, Yoruba, Hausa, Igbo) if offered | Messages change language. Note they are drafts awaiting native-speaker review; log only broken screens, not wording |  | 5 | 2026-11-06
CP-70 | Core platform | Billing | Settings > Billing (only if engineering turns billing on for a test organisation): view the trial, choose a plan, pay with a Paystack test card | Plan changes after payment; an invoice with VAT appears | Paystack test, billing on | 5 | 2026-11-06
CH-01 | Chat (Telegram) | Telegram linking | Account > Telegram: Link Telegram; confirm it is you; open the link on your phone; press Start | The bot says your account is linked | Telegram | 6 | 2026-11-09 | R
CH-02 | Chat (Telegram) | Telegram linking | Open the same link again; open a link older than 10 minutes | Both refused | Telegram | 6 | 2026-11-09
CH-03 | Chat (Telegram) | Telegram linking | Unlink in the web app; send "status" to the bot | The bot no longer acts for you | Telegram | 6 | 2026-11-09
CH-04 | Chat (Telegram) | Chat | Send help, status, "what failed today?" | Correct answers for your organisation; personal data masked | Telegram | 6 | 2026-11-09
CH-05 | Chat (Telegram) | Chat | Send "run <workflow name>"; answer each input; reply yes | Nothing starts before yes; then the run starts and you hear how it ended | Telegram | 6 | 2026-11-09 | R
CH-06 | Chat (Telegram) | Chat | During "run", give a wrong value (letters for an amount); then send cancel | The wrong value is explained and asked again; cancel drops it | Telegram | 6 | 2026-11-09
CH-07 | Chat (Telegram) | Chat | Send "run" with a workflow name that does not exist, or one you may not start | A polite answer; nothing starts | Telegram | 6 | 2026-11-09
CH-08 | Chat (Telegram) | Chat approvals | Start a workflow with an approval; approve with the Approve button on Telegram | The run continues; pressing the same button again does nothing | Telegram | 6 | 2026-11-09 | R
CH-09 | Chat (Telegram) | Chat approvals | An approval that needs step-up; tap Approve | You get a link; it works signed in with passkey or code within 10 minutes; the decision is recorded | Telegram | 6 | 2026-11-09
CH-10 | Chat (Telegram) | Chat approvals | Send "approvals" | Waiting requests are sent again with fresh buttons (three at most) | Telegram | 6 | 2026-11-09
CH-11 | Chat (Telegram) | Chat tables | Send tables; "add to debtors"; answer each column; yes | The row is added with values checked; personal values masked in the reply | Telegram | 6 | 2026-11-09 | R
CH-12 | Chat (Telegram) | Chat tables | Send "find debtors Chidi" | Up to five rows, masked, and how many more | Telegram | 6 | 2026-11-09
CH-13 | Chat (Telegram) | Chat build | Send "build every Friday text my customers who owe me" | Plain steps read back; draft saved only after yes; never published from chat | Telegram, AI key | 6 | 2026-11-09
CH-14 | Chat (Telegram) | Chat money | Send "invoice Ada 25,000 for 5 bags of rice"; give a phone; yes | Invoice shown with the number masked; sent by SMS after yes | Telegram, SMS | 6 | 2026-11-09
CH-15 | Chat (Telegram) | Chat money | Send "spent 12k on diesel at Total" and "cash in 20,000 till" | Each is recorded in the money log after yes | Telegram | 6 | 2026-11-09
CH-16 | Chat (Telegram) | Chat | Belong to two organisations; send "switch"; then "switch <name>" | Lists them; then works in the chosen one; every message starts with its name | Telegram | 6 | 2026-11-09
CH-17 | Chat (Telegram) | Chat | Add the bot to a Telegram group and send "status" there | The bot does not answer in groups | Telegram | 6 | 2026-11-09
CH-18 | Chat (Telegram) | Chat | Send random text, a sticker, a very long message | A polite answer; no crash; no technical words | Telegram | 6 | 2026-11-09
CH-19 | Chat (Telegram) | Chat | Send a voice note (if voice notes are on) | It is understood, or a polite "not available" | Telegram | 6 | 2026-11-09
CH-20 | Chat (Telegram) | Chat roles | As a Viewer, send "run <workflow>" and "add to debtors" | Refused politely, for lack of permission | Telegram, second person | 6 | 2026-11-09
RC-01 | Reconciliation: invoices, payments and money | Invoices | Invoices > New invoice: customer name, phone and email, one amount with a description, due date and note. Save | Saved as Draft with the next number (INV-0001 upwards); a draft can still be changed ¦ |  | 6 | 2026-11-09 | R
RC-02 | Reconciliation: invoices, payments and money | Invoices | New invoice with item lines (3 × ₦2,000 and 1 × ₦5,000) | Total is ₦11,000; each line shows quantity × price and its total ¦ |  | 6 | 2026-11-09
RC-03 | Reconciliation: invoices, payments and money | Invoices | Press Send on a draft | Status Sent. The customer gets an SMS and an email with the invoice link | SMS, email | 6 | 2026-11-09 | R
RC-04 | Reconciliation: invoices, payments and money | Invoices | Press Send again on the same invoice | The same link is sent again; no new number or invoice | SMS, email | 6 | 2026-11-09
RC-05 | Reconciliation: invoices, payments and money | Invoices | Send 6 invoices to the same phone within an hour | The 6th is Sent and works, but no message goes; the invoice says which messages went (5 an hour, 20 a day) | SMS | 6 | 2026-11-09
RC-06 | Reconciliation: invoices, payments and money | Invoice page | Open a draft's link, a made-up link and a mistyped link on a phone | All three say "This invoice was not found" | Phone | 6 | 2026-11-09
RC-07 | Reconciliation: invoices, payments and money | Invoice page | Open a sent invoice's link on a phone | Business name, number, "Awaiting payment", lines, total, paid, still due, due date and note. No customer name, phone or email anywhere | Phone | 7 | 2026-11-10 | R
RC-08 | Reconciliation: invoices, payments and money | Overdue | Make an invoice due today and send it; check it tomorrow (Lagos time) | Becomes Overdue the day after the due date ¦ |  | 7 | 2026-11-10
RC-09 | Reconciliation: invoices, payments and money | Void | Void a sent invoice with a reason | Status Void. Page says "This invoice was cancelled." without the reason; no Pay button ¦ |  | 7 | 2026-11-10
RC-10 | Reconciliation: invoices, payments and money | Paid only by payment | Try to set an invoice to Paid by hand anywhere | Not possible: only a counted payment marks it paid ¦ |  | 7 | 2026-11-10
RC-11 | Reconciliation: invoices, payments and money | VAT | Look for a VAT setting on a business's invoices | None is promised; VAT can only be an ordinary line. Record what the app shows ¦ |  | 7 | 2026-11-10
RC-12 | Reconciliation: invoices, payments and money | Invoice settings | Invoices > Settings: prefix "ADA/"; next number 50; then try to move it back to 10 | New invoices are ADA/0050…; moving back is refused ¦ |  | 7 | 2026-11-10
RC-13 | Reconciliation: invoices, payments and money | Invoice settings | A prefix over 12 characters, or with a space or "#" | Refused ¦ |  | 7 | 2026-11-10
RC-14 | Reconciliation: invoices, payments and money | Amend | On a Sent invoice, Amend > Add a line (₦5,000, "delivery") | New line "Added after the invoice was sent"; total goes up ¦ |  | 7 | 2026-11-10
RC-15 | Reconciliation: invoices, payments and money | Amend | Amend > Give a discount ₦2,000 | Negative line "Discount"; total goes down ¦ |  | 7 | 2026-11-10
RC-16 | Reconciliation: invoices, payments and money | Amend | Amend > Take a line out; try the same line again | Negative "Taken out: …" line; the second is refused ¦ |  | 7 | 2026-11-10
RC-17 | Reconciliation: invoices, payments and money | Amend | On a part-paid invoice (₦10,000 total, ₦6,000 paid) give a ₦5,000 discount | Refused: total cannot go below what was paid; suggests a refund | Paystack test | 7 | 2026-11-10
RC-18 | Reconciliation: invoices, payments and money | Amend | On a paid invoice add a ₦3,000 line | Back to Part-paid with ₦3,000 due | Paystack test | 7 | 2026-11-10
RC-19 | Reconciliation: invoices, payments and money | Amend | Part-paid invoice: discount to exactly what was paid | Becomes Paid; an "invoice paid" workflow starts once | Paystack test | 7 | 2026-11-10
RC-20 | Reconciliation: invoices, payments and money | Amend | Discount the whole remaining total to ₦0 | Refused; void instead ¦ |  | 7 | 2026-11-10
RC-21 | Reconciliation: invoices, payments and money | Amend | Open a Draft | No Amend button: drafts are edited directly ¦ |  | 7 | 2026-11-10
RC-22 | Reconciliation: invoices, payments and money | Amend | Download the invoices export after amendments | The "amended" column shows the net change ¦ |  | 7 | 2026-11-10
RC-23 | Reconciliation: invoices, payments and money | Pay by transfer | Invoice page: Pay this invoice > Pay by bank transfer | Account number, bank, name, amount and "Valid until HH:MM (Lagos time)" | Paystack test | 7 | 2026-11-10
RC-24 | Reconciliation: invoices, payments and money | Pay by transfer | Reload while valid; after expiry press Get a new account number | Same number on reload; a new one after expiry | Paystack test | 7 | 2026-11-10
RC-25 | Reconciliation: invoices, payments and money | Pay by transfer | Pay the shown account in Paystack test; keep the page open | Page updates itself within about 30 seconds: "Paid in full. Thank you." | Paystack test | 7 | 2026-11-10
RC-26 | Reconciliation: invoices, payments and money | Pay by card | Pay by card with a Paystack test card | Paid within about 30 seconds; payment listed with the Paystack reference, matched exactly | Paystack test | 7 | 2026-11-10 | R
RC-27 | Reconciliation: invoices, payments and money | Payment limits | Ask for a new account number or card link more than 5 times in an hour | The page says to try later or contact the business | Paystack test | 7 | 2026-11-10
RC-28 | Reconciliation: invoices, payments and money | Part payments | Settings: Customers may pay part ON. Enter ₦500, then ₦4,000, then leave empty | ₦500 refused (minimum ₦1,000); ₦4,000 gives Part-paid; empty pays the balance | Paystack test | 7 | 2026-11-10 | R
RC-29 | Reconciliation: invoices, payments and money | Part payments | With part payments off, open Pay this invoice | No amount box; always the full balance ¦ |  | 7 | 2026-11-10
RC-30 | Reconciliation: invoices, payments and money | Overpayment | Get a ₦5,000 card link and a full ₦10,000 link; pay both | Paid; an "Overpaid" leak opens for ₦5,000 | Paystack test | 7 | 2026-11-10
RC-31 | Reconciliation: invoices, payments and money | Paid after void | Get a payment link, void the invoice, then pay | Payment counted; a "Paid after it was voided" leak opens | Paystack test | 7 | 2026-11-10
RC-32 | Reconciliation: invoices, payments and money | Transfer fee setting | Set Who pays the transfer fee to The customer | Saved; the amount asked does not change yet (not yet applied) | Paystack test | 7 | 2026-11-10
RC-33 | Reconciliation: invoices, payments and money | Invoice on Telegram | A second person opts in to the business's Telegram updates; send them an invoice | They also get "Invoice INV-… ₦… to pay" with Pay by transfer and Open invoice buttons | Telegram, second person, SMS | 8 | 2026-11-11
RC-34 | Reconciliation: invoices, payments and money | Invoice on Telegram | Customer presses Pay by transfer; after expiry New account number; then Open invoice | Account details with "Valid until"; a new one after expiry; Open invoice gives the link | Telegram, second person, Paystack test | 8 | 2026-11-11
RC-35 | Reconciliation: invoices, payments and money | Invoice on Telegram | Press the buttons on a paid invoice and on a voided one | Paid: "is paid. Thank you!" Void: can no longer be paid | Telegram, second person | 8 | 2026-11-11
RC-36 | Reconciliation: invoices, payments and money | Invoice on Telegram | Customer sends STOP, presses buttons, then START | Buttons stop working after STOP; START brings updates back | Telegram, second person | 8 | 2026-11-11
RC-37 | Reconciliation: invoices, payments and money | Chat invoice | Staff on Telegram: "invoice Ada 25,000 for 5 bags of rice"; then "bill Chi 10k" | Asks for phone or email; shows invoice masked; sends after yes. 10k read as ₦10,000 | Telegram, SMS or email | 8 | 2026-11-11
RC-38 | Reconciliation: invoices, payments and money | Chat invoice | Reply no or cancel instead of yes | Nothing is sent | Telegram | 8 | 2026-11-11
RC-39 | Reconciliation: invoices, payments and money | Suggestions | Invoice for ₦7,500; bring in an unrelated ₦7,500 payment after it was sent (statement line) | Invoices > To match shows a card with the invoice suggested, reason "same amount", and Strong, Likely or Possible | Statement file | 8 | 2026-11-11
RC-40 | Reconciliation: invoices, payments and money | Suggestions | Statement line whose description is "inv0104" with a different amount | The INV-0104 suggestion says the reference names the invoice | Statement file | 8 | 2026-11-11
RC-41 | Reconciliation: invoices, payments and money | Suggestions | Money dated before the invoice was sent | That invoice is never suggested | Statement file | 8 | 2026-11-11
RC-42 | Reconciliation: invoices, payments and money | Confirm | On a card press Match | Paid or Part-paid; payment shows "Suggested, confirmed by <you>"; other suggestions close | Statement file | 8 | 2026-11-11 | R
RC-43 | Reconciliation: invoices, payments and money | Reject | Press Not this one | Gone and never offered again; with none left the money moves under No invoice suggested | Statement file | 8 | 2026-11-11
RC-44 | Reconciliation: invoices, payments and money | Match by hand | Match to another invoice… and pick one not suggested | Counted; "Matched by hand". Only sent, unpaid invoices listed | Statement file | 8 | 2026-11-11
RC-45 | Reconciliation: invoices, payments and money | Undo | On the invoice press Undo on that payment | Invoice back to its earlier status; history keeps both; money returns to To match | Statement file | 8 | 2026-11-11 | R
RC-46 | Reconciliation: invoices, payments and money | Two people at once | Two people open the same To match card; one matches, then the other | The second is told it is already matched | Second person | 8 | 2026-11-11
RC-47 | Reconciliation: invoices, payments and money | Match on Telegram | A payment that is not an exact match arrives | Message "Is this for INV-…?" with reasons, no names, and Yes, match / No | Telegram, statement file | 8 | 2026-11-11
RC-48 | Reconciliation: invoices, payments and money | Match on Telegram | Press Yes, match; on another press No | Yes: matched and status given. No: next suggestion or a web link | Telegram | 8 | 2026-11-11
RC-49 | Reconciliation: invoices, payments and money | Match on Telegram | Decide in the web app first, then press the Telegram button | "Already matched" or "Already turned down" | Telegram | 8 | 2026-11-11
RC-50 | Reconciliation: invoices, payments and money | Split | Customer with ₦20,000 (older) and ₦30,000 invoices; ₦60,000 comes in; Split across the customer's invoices | Older first, then newer, editable. The ₦10,000 left becomes credit | Statement file | 8 | 2026-11-11 | R
RC-51 | Reconciliation: invoices, payments and money | Split | Split by hand with parts adding to more than the payment | Refused; shows what is left | Statement file | 8 | 2026-11-11
RC-52 | Reconciliation: invoices, payments and money | Split | Undo one part of a split | Only that invoice goes back | Statement file | 8 | 2026-11-11
RC-53 | Reconciliation: invoices, payments and money | Customer credit | After RC-50, open The customer's money; send them a ₦15,000 invoice | Credit ₦10,000 shown; on Send it pays ₦10,000 and the message says ₦5,000 is left | SMS or email | 8 | 2026-11-11
RC-54 | Reconciliation: invoices, payments and money | Customer account number | The customer's money > Give this customer an account number (Paystack); repeat | Issued; repeating shows the same account | Paystack test | 8 | 2026-11-11
RC-55 | Reconciliation: invoices, payments and money | Customer account number | Enter one by hand; then register the same number for another customer | First registered; second refused ¦ |  | 8 | 2026-11-11
RC-56 | Reconciliation: invoices, payments and money | Customer account number | Pay into it more than the oldest invoice | Matched with nobody asked: oldest first, rest as credit | Paystack test (may not be possible) | 8 | 2026-11-11
RC-57 | Reconciliation: invoices, payments and money | Payer memory | Confirm a payment carrying a payer name; later the same payer pays again for a new invoice | Suggestion says "this payer paid for this customer before" (Strong) | Payment with a payer name | 8 | 2026-11-11
RC-58 | Reconciliation: invoices, payments and money | Payer memory | Press Forget this payer; same payer pays again | No payer reason any more | Payment with a payer name | 8 | 2026-11-11
RC-59 | Reconciliation: invoices, payments and money | Automatic matching | Settings: Match strong suggestions automatically ON; bring in a payment with the same amount and a reference naming the invoice | Matched without asking; "Matched automatically"; Undo works | Statement file | 9 | 2026-11-12
RC-60 | Reconciliation: invoices, payments and money | Automatic matching | Auto ON; two open invoices with the same amount; bring that amount in | Left for a person | Statement file | 9 | 2026-11-12
RC-61 | Reconciliation: invoices, payments and money | Automatic matching | Auto OFF; repeat RC-59 | Stays a suggestion | Statement file | 9 | 2026-11-12
RC-62 | Reconciliation: invoices, payments and money | Refunds | Refund a card payment that paid an invoice, from the Paystack test dashboard | A refund (out) in the money log; owners told once. Record whether the invoice reopens: the docs disagree | Paystack test, Telegram | 9 | 2026-11-12 | R
RC-63 | Reconciliation: invoices, payments and money | Refunds | Partial refund of a matched payment | The rest waits in To match with a note that part went back | Paystack test | 9 | 2026-11-12
RC-64 | Reconciliation: invoices, payments and money | Recorded once | One payment with both the webhook and polling running | Exactly one money log entry | Paystack test | 9 | 2026-11-12 | R
RC-65 | Reconciliation: invoices, payments and money | Kept tables | Open money_log and money_matches under Tables; try to add, edit or delete | Readable and exportable; every change refused ¦ |  | 9 | 2026-11-12
RC-66 | Reconciliation: invoices, payments and money | Invoice paid trigger | Workflow from "Send a receipt when an invoice is paid"; publish; pay an invoice | One run within seconds; customer thanked; owner told | Paystack test, SMS or email | 9 | 2026-11-12
RC-67 | Reconciliation: invoices, payments and money | Invoice paid trigger | Undo the payment and pay again; add another payment to a paid invoice | No second run for that invoice | Paystack test | 9 | 2026-11-12
RC-68 | Reconciliation: invoices, payments and money | Payment trigger | Workflow "When a payment is counted towards one of your invoices"; make a 2-part split | One run per part | Statement file | 9 | 2026-11-12
RC-69 | Reconciliation: invoices, payments and money | Live only | The same workflow published to dev only | Nothing starts when an invoice is paid | Paystack test | 9 | 2026-11-12
RC-70 | Reconciliation: invoices, payments and money | Templates | "Send an invoice and hear when it is paid" and "Chase overdue invoices every day"; run the chase twice in a day | Send-invoice continues once paid. One reminder per period; no duplicate on the second run | SMS or email | 9 | 2026-11-12
RC-71 | Reconciliation: invoices, payments and money | Ready to publish | Publish a workflow using Paystack transfer collection before any transfer account exists | Not blocked; note "Ask Paystack support" ¦ |  | 9 | 2026-11-12
RC-72 | Reconciliation: invoices, payments and money | Statement upload | Money > Upload statement (account "gtbank/current") with ins and outs | "N added, 0 skipped"; lines in the log under your name; ins offered in To match | Statement file | 9 | 2026-11-12 | R
RC-73 | Reconciliation: invoices, payments and money | Statement upload | Upload the same file again, then an overlapping one | Existing lines skipped and counted; new ones added | Statement file | 9 | 2026-11-12
RC-74 | Reconciliation: invoices, payments and money | Statement upload | A bank-style file (separate Money in / Money out, dates like 23-Oct-2026, 1,234.50 DR, (1,234.50)); map the columns; upload a second from the same bank | Mapping form guessed from the column names; amounts read right; the second needs no mapping | Statement file | 9 | 2026-11-12
RC-75 | Reconciliation: invoices, payments and money | Statement upload | A file with one unreadable line | Nothing added; the bad line listed with the reason | Statement file | 9 | 2026-11-12
RC-76 | Reconciliation: invoices, payments and money | Cash and expenses | Money > Cash and expenses: an expense, a cash in, a cash out; press submit twice fast | Each recorded once, under your name ¦ |  | 9 | 2026-11-12
RC-77 | Reconciliation: invoices, payments and money | Cash by chat | "spent 12,000 on diesel at Total", "expense 5000 fuel", "cash in 20,000 till", "cash out 3,000 float"; yes to each; Yes twice on one | Each recorded once; diesel under fuel | Telegram | 9 | 2026-11-12
RC-78 | Reconciliation: invoices, payments and money | Money overview | Money > Overview: Today, This week, This month, custom dates (try over 400 days) | Money in and out, pending, invoices paid, leaks, by channel; over 400 days refused ¦ |  | 9 | 2026-11-12
RC-79 | Reconciliation: invoices, payments and money | Home money card | Home after today's payments | Money in, count, money out, waiting to be matched ¦ |  | 9 | 2026-11-12
RC-80 | Reconciliation: invoices, payments and money | Daily summary | Next morning after 08:00 Lagos, owner on Telegram | One message "Yesterday: ₦… in; ₦… out; … invoices paid" with the Money link. Nothing after a quiet day | Telegram | 10 | 2026-11-13
RC-81 | Reconciliation: invoices, payments and money | Daily summary | Settings > Notifications: owner turns the summary off; an operator turns it on | Owner gets none from next day; the operator starts getting it | Telegram, second person | 10 | 2026-11-13
RC-82 | Reconciliation: invoices, payments and money | Monthly email | On the 1st of the month after 09:00 Lagos | Email "money in <month>" with totals and the Money link | Email | 10 | 2026-11-13
RC-83 | Reconciliation: invoices, payments and money | Export: money log | Download the month's money log | One line per movement; ins positive, outs negative; naira with 2 decimals; matched invoice numbers ¦ |  | 10 | 2026-11-13 | R
RC-84 | Reconciliation: invoices, payments and money | Export: invoices | Download invoices with and without "with customers' names" (owner, then viewer) | Names only when ticked by someone allowed; phones and emails never ¦ |  | 10 | 2026-11-13
RC-85 | Reconciliation: invoices, payments and money | Export: journal | Download the accounting journal | Each movement balances (debits = credits) with sensible accounts ¦ |  | 10 | 2026-11-13
RC-86 | Reconciliation: invoices, payments and money | Export safety | Statement line with description "=SUM(A1)"; export | Shown as text with a leading apostrophe, never run | Statement file | 10 | 2026-11-13
RC-87 | Reconciliation: invoices, payments and money | Leak: unmatched | Leave money in unmatched for over a day | Leak "Money in with nothing to match" with a plain sentence. Cash never a leak | Statement file | 10 | 2026-11-13
RC-88 | Reconciliation: invoices, payments and money | Leak: overdue | Overdue invoice, then part-pay it | Leak for what is due; lowers with the part payment; closes when paid | Paystack test | 10 | 2026-11-13
RC-89 | Reconciliation: invoices, payments and money | Closing leaks | Assign a leak; close one Recovered (amount and note), one Written off, one Not a leak; try to edit a closed one | Recovered total rises; closed leaks show how and by whom; cannot be changed | Second person | 10 | 2026-11-13
RC-90 | Reconciliation: invoices, payments and money | Agreed fees | Money > Fees: Paystack 1.5% + ₦100, cap ₦2,000 | Saved; no false fee leak ¦ |  | 10 | 2026-11-13
RC-91 | Reconciliation: invoices, payments and money | Permissions | Sign in as Viewer or Auditor | Can see invoices, To match, Money and leaks. Cannot create, send, void, amend, match, undo, upload, enter cash or close leaks | Second person | 10 | 2026-11-13 | R
RC-92 | Reconciliation: invoices, payments and money | Permissions | Viewer sends "invoice Ada 5000" or "spent 500 on fuel" on Telegram | Refused | Telegram, second person | 10 | 2026-11-13
RC-93 | Reconciliation: invoices, payments and money | Permissions | Operator does the manage actions | Allowed | Second person | 10 | 2026-11-13
RC-94 | Reconciliation: invoices, payments and money | Permissions | Someone with reveal shows a customer's name on an invoice | Shown and recorded in the audit log ¦ |  | 10 | 2026-11-13
RC-95 | Reconciliation: invoices, payments and money | Paying people | "Pay a supplier after approval": pick bank, type account number, check name, approve; run again for the same account | First approval warns "First payment to this account"; payout in the money log; second has no warning; never pays twice | Paystack test, second person | 10 | 2026-11-13
SF-01 | Storefronts, orders, bookings, forms and agents | Page editor access | Sign in as owner, then as admin, then as a plain member, and open the Storefront page each time | Owner and admin can open and edit it. A member without storefront.manage cannot | Second person | 11 | 2026-11-16
SF-02 | Storefronts, orders, bookings, forms and agents | Draft and address | Fill in name, tagline, about, area/address, hours and an address such as ada-test-kitchen, then Save | Saved as a draft. Nothing is visible at that address on the preview domain yet ¦ |  | 11 | 2026-11-16
SF-03 | Storefronts, orders, bookings, forms and agents | Address rules | Try the addresses "ab" (too short), a 31-character one, "my_shop!", "taskiem", "gtbank", "g7bank" and "paystack" | Each is refused: 3 to 30 letters, digits and hyphens only; reserved names and look-alikes are not allowed ¦ |  | 11 | 2026-11-16
SF-04 | Storefronts, orders, bookings, forms and agents | Refused at publishing | Put a website link, an email address and a non-Nigerian phone number in the about text, then Publish | The publish is refused with a plain reason. Fix them and it publishes | Telegram | 11 | 2026-11-16
SF-05 | Storefronts, orders, bookings, forms and agents | Make my catalogue | Press Make my catalogue, add 3 items with a name, a naira price and a photo, delete one, and never open Tables | Items appear in the editor. No Tables page is needed. Prices are in naira ¦ |  | 11 | 2026-11-16
SF-06 | Storefronts, orders, bookings, forms and agents | Use a table you already have | Under "Use a table you already have", pick a table and match name, price, category, photo, available and sort. Then try to match a phone or email column | Matching works. Personal columns are never offered, or are refused ¦ |  | 11 | 2026-11-16
SF-07 | Storefronts, orders, bookings, forms and agents | Photos | Upload a sideways phone photo (with location on) as a product photo and as the logo; then upload a file that is not an image renamed .jpg | Shown upright. Location and camera details removed. The non-image is refused | Phone | 11 | 2026-11-16
SF-08 | Storefronts, orders, bookings, forms and agents | Look | On Storefront > Look, switch between Clean, Bold and Editorial, pick a very light colour, and leave the logo empty | The preview shows the page, order form, booking page and form in that look before saving. With no logo, the initials show. Text stays readable. After Save, the live page changes within 30 seconds ¦ |  | 11 | 2026-11-16
SF-09 | Storefronts, orders, bookings, forms and agents | Look reaches every page | After changing the look, open the order form, a status page, a hosted form and a not-found address | All of them use the same theme and colour ¦ |  | 11 | 2026-11-16
SF-10 | Storefronts, orders, bookings, forms and agents | Close for now / Reopen | Close the page with a message over 200 characters, then with one containing a link, then with a valid one, then press Reopen | Over 200 characters and links are refused. A closed page shows the message and the business card but no catalogue. Reopen brings the catalogue back ¦ |  | 11 | 2026-11-16
SF-11 | Storefronts, orders, bookings, forms and agents | Address change | Change the address of a published page and publish again | The new address serves the page. The old address stops serving ¦ |  | 11 | 2026-11-16
SF-12 | Storefronts, orders, bookings, forms and agents | QR and printable card | Open the QR code and print the card. Visit <your page address>/qr.png. Try qr.png on a draft-only page | The QR scans to the page. The card shows name, QR, address and phone. A draft has no QR | Phone | 11 | 2026-11-16
SF-13 | Storefronts, orders, bookings, forms and agents | Public page content | Open the published page in a private (incognito) window on your phone | Card with Call, Chat on WhatsApp and directions link (no embedded map); "Open now" or "Closed now" correct for Lagos time; catalogue grouped by category with ₦ prices; unavailable items marked; safety line and Report this page in the footer | Phone | 11 | 2026-11-16 | R
SF-14 | Storefronts, orders, bookings, forms and agents | No JavaScript | Turn JavaScript off in the browser and browse, order and report | Everything still works ¦ |  | 11 | 2026-11-16 | R
SF-15 | Storefronts, orders, bookings, forms and agents | No cookies | In the browser's developer tools (Application > Cookies), check the storefront, order form and hosted form | No cookies are set on public pages | Developer tools | 11 | 2026-11-16
SF-16 | Storefronts, orders, bookings, forms and agents | 3G speed | On a low-end Android phone, or Chrome set to "Slow 3G", open the page fresh | Usable in about 3 seconds. Images load as you scroll | Phone | 11 | 2026-11-16
SF-17 | Storefronts, orders, bookings, forms and agents | Link preview card | Paste the page link into a Telegram chat | A preview card with name, tagline and logo | Telegram | 11 | 2026-11-16
SF-18 | Storefronts, orders, bookings, forms and agents | Catalogue refresh | Change a price in the table, then press Refresh. Separately, change a row and wait 15 minutes | Refresh shows the new price at once. The 15-minute automatic refresh picks up the change ¦ |  | 11 | 2026-11-16
SF-19 | Storefronts, orders, bookings, forms and agents | Not framed | Ask a developer to put the page address inside a frame on another website | Refused (framing only on proven websites) | Developer | 11 | 2026-11-16
SF-20 | Storefronts, orders, bookings, forms and agents | Set up the order form | Storefront > Forms > Order > Set up. Choose pickup and delivery with a note, and payment after the owner accepts | The default workflow is added and published. The page gains an order button ¦ |  | 12 | 2026-11-17 | R
SF-21 | Storefronts, orders, bookings, forms and agents | One-person business order | In a business with only an owner, place an order as a customer; the owner accepts in Approvals | The owner sees "You are the only person who can approve this" and can accept. Not stuck or declined after 24 hours | SMS | 12 | 2026-11-17
SF-22 | Storefronts, orders, bookings, forms and agents | Order: pay after accepting | Customer orders 2 items with name, Nigerian phone and email. Owner accepts on Telegram. Customer pays with a Paystack test card | Customer sees a status page with a reference (AK-XXXXXX). Owner gets accept or decline with items, total and collection. After accept, an SMS and email with a payment link. After paying, the customer is told it is paid | Telegram, Paystack test, SMS, email | 12 | 2026-11-17 | R
SF-23 | Storefronts, orders, bookings, forms and agents | Mark delivered | After payment, the owner answers "mark delivered or collected" | The order becomes completed | Telegram | 12 | 2026-11-17
SF-24 | Storefronts, orders, bookings, forms and agents | Decline | Owner declines an unpaid order | The customer is texted. Status is declined | Telegram, SMS | 12 | 2026-11-17
SF-25 | Storefronts, orders, bookings, forms and agents | No answer in a day | Leave an owner request unanswered for 24 hours | The order is declined automatically and the customer is texted | SMS | 12 | 2026-11-17
SF-26 | Storefronts, orders, bookings, forms and agents | Unpaid after accept | Accept an order and do not pay the link for a day | The order expires and the customer is told | Paystack test, SMS | 12 | 2026-11-17
SF-27 | Storefronts, orders, bookings, forms and agents | Pay when ordering | Verified business: set Payment = when ordering. Customer orders and pays | Checkout opens at once. After paying, the customer returns to the status page; it shows paid within about 30 seconds; only then is the owner asked | Paystack test, operator | 12 | 2026-11-17 | R
SF-28 | Storefronts, orders, bookings, forms and agents | Unpaid at order expires | Payment = when ordering. The customer abandons checkout | After 30 minutes the order expires; no owner request starts | Paystack test | 12 | 2026-11-17
SF-29 | Storefronts, orders, bookings, forms and agents | Pay at order needs verification | Unverified business tries to set Payment = when ordering | Not allowed until the business is verified ¦ |  | 12 | 2026-11-17
SF-30 | Storefronts, orders, bookings, forms and agents | No online payment | Set "no online payment" and place an order | No payment link is sent. The order goes on to accept and complete | SMS | 12 | 2026-11-17
SF-31 | Storefronts, orders, bookings, forms and agents | Order form checks | On the order form try: a non-Nigerian phone, a card number in the note, submitting within 1 to 2 seconds of opening, then many quick submits | Each is refused in plain words or slowed down ¦ |  | 12 | 2026-11-17
SF-32 | Storefronts, orders, bookings, forms and agents | Price comes from the catalogue | Ask a developer to change a price inside the submitted form | The total uses the catalogue price, not the form's | Developer | 12 | 2026-11-17
SF-33 | Storefronts, orders, bookings, forms and agents | Stock shown and capped | Map a stock column. Set one item's stock to 2 and another's to 0 | The 0-stock item shows sold out and cannot be ordered. The form offers no more than 2; an order for 3 is refused ¦ |  | 12 | 2026-11-17 | R
SF-34 | Storefronts, orders, bookings, forms and agents | Stock lowered on accept | Two customers order the last unit each. The owner accepts both | Stock never goes below 0. The second order's note says what was short | Second person | 12 | 2026-11-17
SF-35 | Storefronts, orders, bookings, forms and agents | Price check | Customer orders; within seconds the owner raises the price in the table | The order waits. The customer gets an SMS with the new total and a link to confirm or cancel. Confirm and it proceeds; left a day, it expires | SMS | 12 | 2026-11-17
SF-36 | Storefronts, orders, bookings, forms and agents | Price check: item gone | As SF-35, but delete every ordered item from the table | The order is cancelled and the customer told | SMS | 12 | 2026-11-17
SF-37 | Storefronts, orders, bookings, forms and agents | Orders list | Open Storefront > Orders as owner, then as a member without the reveal permission | Newest first, customer details masked. Show details works only with the permission (and is in the audit log) | Second person | 12 | 2026-11-17
SF-38 | Storefronts, orders, bookings, forms and agents | Questions and call-backs | Set up both forms. As a customer, send a question and a call-back request | Customer gets an acknowledgement SMS. Owner is asked to mark it answered or called back | Telegram, SMS | 12 | 2026-11-17
SF-39 | Storefronts, orders, bookings, forms and agents | Customer SMS | Read the customer SMS messages received | Each starts with the business name and is in the business's language | SMS | 12 | 2026-11-17
SF-40 | Storefronts, orders, bookings, forms and agents | SMS flood limit | From one phone number, place more than 5 orders in an hour | Texts to that number stop after 5 an hour (20 a day); the orders are still recorded | SMS | 12 | 2026-11-17
SF-41 | Storefronts, orders, bookings, forms and agents | Money matched | Open a paid order's page | Under "Money matched", the Paystack payment shows as matched | Paystack test | 12 | 2026-11-17
SF-42 | Storefronts, orders, bookings, forms and agents | Refund through the workflow | Pay-at-order order: owner declines, then approves "Refund the customer?" | Status refund due, then refunded. Customer told money arrives in 5 to 10 working days. Refund shows in Paystack test | Paystack test, Telegram, SMS | 12 | 2026-11-17 | R
SF-43 | Storefronts, orders, bookings, forms and agents | Refund later in chat | Decline a paid order, reject the refund prompt, then send "refund AK-XXXXXX" and reply yes | Refunded. A second refund of the same order is refused | Telegram, Paystack test | 12 | 2026-11-17
SF-44 | Storefronts, orders, bookings, forms and agents | Refund in the web app | On a refund-due order press Refund through Paystack | Refunded; if Paystack refuses, it stays refund due with Paystack's reason | Paystack test | 12 | 2026-11-17
SF-45 | Storefronts, orders, bookings, forms and agents | Bookings set-up | Storefront > Bookings: services of 30 and 60 minutes, one with no price, one class with room for 3, a 10-minute buffer, a lunch break, a day off, 30 days ahead, 2 hours' notice. Set up the booking form | Services listed; "Price on the day" where no price. Free times match hours, length and buffer. None on the day off or within 2 hours ¦ |  | 13 | 2026-11-18
SF-46 | Storefronts, orders, bookings, forms and agents | Book a time | Customer books a service. Owner accepts on Telegram | Customer gets an SMS that it is booked, with a link to move or cancel | Telegram, SMS | 13 | 2026-11-18 | R
SF-47 | Storefronts, orders, bookings, forms and agents | No double booking | Two people on two phones pick the same single slot and press send together | Only one gets it; the other is told it is taken. A class for 3 takes 3, then closes | Second person, phone | 13 | 2026-11-18 | R
SF-48 | Storefronts, orders, bookings, forms and agents | Customer moves or cancels | From the link, move a booking. Then try to cancel inside the 2-hour cut-off | The move works and the owner is told. The late cancel is refused | SMS, Telegram | 13 | 2026-11-18
SF-49 | Storefronts, orders, bookings, forms and agents | Owner booking commands | Send bookings, today, "move AD-XXXXXX to Sat 11:00", "booking AD-XXXXXX cancel", "off 25 Dec"; confirm each with yes | Each shown, then applied on yes. The customer is told. The day off removes free times | Telegram, SMS | 13 | 2026-11-18
SF-50 | Storefronts, orders, bookings, forms and agents | Reminders and attendance | Book a slot just over a day ahead and leave it | Reminders a day before and 2 hours before. Afterwards the owner is asked if they came. The owner's 07:00 day list arrives | Telegram, SMS | 13 | 2026-11-18
SF-51 | Storefronts, orders, bookings, forms and agents | Paid booking cancelled | Payment when booking (deposit). Customer cancels: once by default, once with Keep the deposit | Default: refund due. Keep the deposit: no refund | Paystack test, SMS | 13 | 2026-11-18
SF-52 | Storefronts, orders, bookings, forms and agents | make my page | New business with no page: send "make my page", answer the questions (skip one, but not the name), send a photo, answer yes | Draft at a free address; a products table made; on yes: link, QR image and a status text, then "Turn on orders?" | Telegram | 13 | 2026-11-18 | R
SF-53 | Storefronts, orders, bookings, forms and agents | turn on orders | Reply yes to "Turn on orders?" (or send "turn on orders") | Order workflow published, form on, page republished. With no Paystack: no online payment, plus a link to connect it | Telegram | 13 | 2026-11-18
SF-54 | Storefronts, orders, bookings, forms and agents | my page | Send "my page" | Link, status (draft, published or closed) and today's orders | Telegram | 13 | 2026-11-18
SF-55 | Storefronts, orders, bookings, forms and agents | add product | Send "add product Jollof rice 2k", a photo captioned "Fried rice ₦2,500", and "add product Jollof rice 3000" | First two added on yes with prices read correctly. The duplicate is refused with a hint to use price | Telegram | 13 | 2026-11-18
SF-56 | Storefronts, orders, bookings, forms and agents | Item commands | "price jollof 2500", "hide jollof", "show jollof", "stock jollof 5", and a word matching 2 items | Old and new shown, applied on yes. Two matches give a numbered list. no or cancel drops it | Telegram | 13 | 2026-11-18
SF-57 | Storefronts, orders, bookings, forms and agents | hours | "hours mon-sat 8-6, closed sunday", then "hours open 24 hours" | Saved and republished. 8-6 reads as 08:00 to 18:00 | Telegram | 13 | 2026-11-18
SF-58 | Storefronts, orders, bookings, forms and agents | add service | "add service Haircut 45min 2000" | Services table made if needed; service added; page republished | Telegram | 13 | 2026-11-18
SF-59 | Storefronts, orders, bookings, forms and agents | close shop | "close shop back on monday", "open shop", then "close shop today" | Closes with the message, reopens. "today" reopens at 06:00 Lagos the next day | Telegram | 13 | 2026-11-18
SF-60 | Storefronts, orders, bookings, forms and agents | orders by chat | "orders", "order AK-XXXXXX", "order AK-XXXXXX ready", "order AK-XXXXXX collected" | Ten newest, masked. ready texts the customer; collected completes the order | Telegram, SMS | 13 | 2026-11-18
SF-61 | Storefronts, orders, bookings, forms and agents | qr and publish | "qr", then edit in the web app and send "publish", then yes | QR image and address. The draft goes live | Telegram | 13 | 2026-11-18
SF-62 | Storefronts, orders, bookings, forms and agents | Chat permissions | A member without storefront rights sends "close shop" | Refused | Telegram, second person | 13 | 2026-11-18
SF-63 | Storefronts, orders, bookings, forms and agents | Phone confirmed first | A new business with no linked Telegram tries to Publish | Refused until Telegram (or WhatsApp) is linked | Telegram | 14 | 2026-11-19
SF-64 | Storefronts, orders, bookings, forms and agents | First publish held | Unverified business publishes for the first time; operator approves in the console. Repeat with reject and a note | Waits for review, not shown. Approve: live and owner told. Reject: back to draft, owner told | Operator, Telegram | 14 | 2026-11-19 | R
SF-65 | Storefronts, orders, bookings, forms and agents | Blocked words and prices | Publish a product named "d0uble your money", one with "tramadol", a ₦0 item and one above ₦10,000,000 | Blocked word refused; flagged words and odd prices wait for review | Operator | 14 | 2026-11-19
SF-66 | Storefronts, orders, bookings, forms and agents | Report this page | Report the page with JavaScript off. Report 4 times in a day from one connection | Report accepted. The 4th from the same connection is refused (3 a day) ¦ |  | 14 | 2026-11-19
SF-67 | Storefronts, orders, bookings, forms and agents | Suspended by reports | Three different people (different phones and networks) report one page | Within minutes: "This page is unavailable", forms take nothing, owner told on Telegram | 3 people, Telegram | 14 | 2026-11-19
SF-68 | Storefronts, orders, bookings, forms and agents | Appeal and restore | Owner replies "APPEAL I sell food only"; tries to publish, close or reopen while suspended | Those are refused. The appeal is in the operator queue. Approve restores the page | Telegram, operator | 14 | 2026-11-19
SF-69 | Storefronts, orders, bookings, forms and agents | Business verification | Ask to verify the business (legal name, address, CAC number) | Shows waiting. Operator approves: the Verified badge appears and pay-at-order unlocks | Operator | 14 | 2026-11-19
SF-70 | Storefronts, orders, bookings, forms and agents | Paused orders | Unverified business: 50 orders and bookings in one Lagos day (or the operator lowers the limit) | Forms say "not taking orders online right now". Owner told once. Lifts next day or on verification | Operator | 14 | 2026-11-19
SF-71 | Storefronts, orders, bookings, forms and agents | Field agent sign-up | Operator registers an agent. Agent signs in on a phone, New business, owner's phone; owner sends "AGREE <code>" to the bot and taps Share my number. Try 5 wrong codes and a code over 30 minutes old | Works only from the owner's own number. 5 wrong codes lock it; 30 minutes expires it; New code makes a fresh one. Agent edits under a banner with time left. Record visit marks agent onboarded. Publishing ends the session | Operator, Telegram, second person, phone | 14 | 2026-11-19 | R
SF-72 | Storefronts, orders, bookings, forms and agents | Agent limits and STOP AGENT | During a session the agent tries to open orders or members. Owner sends "STOP AGENT". Then Members > Invite an agent back for 1 hour | Orders and members refused. STOP AGENT ends the session at once. The invite works at once and ends after an hour | Telegram, second person | 14 | 2026-11-19
SF-73 | Storefronts, orders, bookings, forms and agents | Own domain (if a real domain is available) | Storefront > Your own domain: add a domain you control; follow the registrar guide; Check now before and after adding the records. Also try an IP address and "com.ng" | Check now names what is missing in plain words. Once verified the page serves there. Bad entries refused | Real domain | 14 | 2026-11-19
SF-74 | Storefronts, orders, bookings, forms and agents | On your website (if available) | Add a website, Send to my web designer (an email), then Check now | The designer gets the code by email. After proof, the page shows inside that site only | Real domain, email | 14 | 2026-11-19
SF-75 | Storefronts, orders, bookings, forms and agents | Hosted form with phone code | Publish a public form that checks the phone. Enter 6 wrong codes; try a code over 10 minutes old; double-tap submit | Five tries; 10-minute expiry; a double tap gives one reference. Report this form in the footer | SMS | 14 | 2026-11-19
SF-76 | Storefronts, orders, bookings, forms and agents | Get updates on Telegram | On a form's thank-you page tap Get updates on Telegram, Start, share the number. Later send STOP, then START | Later messages arrive in Telegram. After STOP they come by SMS. START restores Telegram | Telegram, SMS | 14 | 2026-11-19
SC-01 | Schools | Turning it on | As Owner A, turn Schools on under Secrets & settings (or Schools > Settings) | Schools appears in the menu. A Bursar role is offered or added. The change is in the audit log ¦ |  | 16 | 2026-11-23
SC-02 | Schools | Turning it off | With classes, students and invoices in place, turn Schools off; open a Schools page by its address; turn it back on | Off: the menu item is gone and pages say the area is off. On again: everything is back as before. Both changes audited ¦ |  | 16 | 2026-11-23
SC-03 | Schools | Only an owner | As an admin who is not an owner, try to turn Schools on or off | Not allowed | Second person (admin) | 16 | 2026-11-23
SC-04 | Schools | Bursar role | Give someone Bursar under Members & keys. As the Bursar: add a student, post cash, send a reminder. Then try approvals, Clear by override, deciding a payment plan, and the thresholds in Schools > Settings | The first three work. The approval actions and the settings are not available | Second person (Bursar) | 16 | 2026-11-23
SC-05 | Schools | Viewer | Sign in as a Viewer or Auditor | Students, Debtors, Clearance and Receipts can be seen. Add a student, Post a payment and Invoice the term are not available | Second person (Viewer) | 16 | 2026-11-23
SC-06 | Schools | Gate role | Owner gives someone the Gate role. They sign in on a phone and type other addresses such as /invoices, /settings and /schools/students | They land on the gate screen with no menu. Every other page is refused. Only signing out and the gate screen work | Phone, second person (Gate) | 16 | 2026-11-23 | R
SC-07 | Schools | Gate role | As an admin who is not an owner, try to give someone the Gate role | Refused: only an owner can | Second person (admin) | 16 | 2026-11-23
SC-08 | Schools | Personal data | Open Students, Families, Debtors and Receipts without the reveal permission. Then with it press Show names (and Show personal details). Check the audit log | Names, phones and dates of birth masked until shown. Each Show is in the audit log. Without the permission the buttons are absent | Second person | 16 | 2026-11-23
SC-09 | Schools | Search | Search students by part of a name while names are masked, then by admission number | A name search needs names shown. Admission number search always works ¦ |  | 16 | 2026-11-23
SC-10 | Schools | Classes | Add JSS 1 A, JSS 1 B, JSS 2 A, JSS 3 A and Nursery A with their order. Then add JSS 1 A again | The duplicate is refused. Arms of one class share its order ¦ |  | 16 | 2026-11-23
SC-11 | Schools | Classes | Remove a class no student was ever in; then try to remove one that has history | The first is removed. The second is refused ¦ |  | 16 | 2026-11-23
SC-12 | Schools | Sessions | Add session 2026/2027, then add it again | The second is refused ¦ |  | 16 | 2026-11-23
SC-13 | Schools | Terms | Add First, Second and Third term with start, end and fees-due dates. Edit and remove a term that has not started | Both work ¦ |  | 16 | 2026-11-23
SC-14 | Schools | Start a term | On First term press Start | It becomes current; every active student is enrolled in their class; audited ¦ |  | 16 | 2026-11-23 | R
SC-15 | Schools | Start a term | Press Start on the same term again | Nobody is enrolled twice ¦ |  | 16 | 2026-11-23
SC-16 | Schools | Term rules | Start Second term; try to change First term, its enrolments and its fees | First term is past and read-only. Only one term is current ¦ |  | 16 | 2026-11-23
SC-17 | Schools | Enrolment | While a term runs, add a student; move one from JSS 1 A to JSS 1 B; open the moved student's page | New student enrolled at once. The move carries the enrolment. Class history shows; past terms keep the old class ¦ |  | 16 | 2026-11-23
SC-18 | Schools | Import students | Students > Import students: a good CSV with other headings (student, adm no, parent, parent phone, relation, dob) and dates like 21/03/2015. Check the file | A preview shows students added and updated, and families grouped by guardian phone. Nothing saved until Save | CSV file | 16 | 2026-11-23 | R
SC-19 | Schools | Import: families | In the CSV put two siblings with the same guardian phone, and one student on two lines with two guardians | Siblings become one family. The student on two lines has two guardians | CSV file | 16 | 2026-11-23
SC-20 | Schools | Import: formats | Write classes as "jss-1 a" or "JSS1A"; phones as 08031234567, +2348031234567 and a +44 number | All accepted | CSV file | 16 | 2026-11-23
SC-21 | Schools | Import: bad rows | A 20-line file with one bad line of each kind: no name, no phone, a phone that is not a number, an unknown class, one admission number with two names, one phone for two guardians | Nothing saved. Each bad line listed with its reason. Fixed, it saves | CSV file | 16 | 2026-11-23 | R
SC-22 | Schools | Import: again | Re-import the same file with one name and one class changed | Students updated by admission number; nobody added twice | CSV file | 16 | 2026-11-23
SC-23 | Schools | Admission number | Add "gca/001" when "GCA/001" exists | Refused (case does not count) ¦ |  | 16 | 2026-11-23
SC-24 | Schools | One family per phone | Add a guardian to family B with a phone already in family A | Refused ¦ |  | 16 | 2026-11-23
SC-25 | Schools | Add a student | Students > Add a student with name, admission number, class, optional date of birth and a new guardian | Saved with a new family; audited ¦ |  | 16 | 2026-11-23
SC-26 | Schools | Promotion | Classes and terms > Promotion: mark one repeats, one leaves, one graduates early; promote | Others move up a class; the last class graduates; the leaver is withdrawn; counts update as you choose ¦ |  | 19 | 2026-11-26
SC-27 | Schools | Promotion | Promote the same session again; try after the next session's first term has started | Both refused ¦ |  | 19 | 2026-11-26
SC-28 | Schools | Fees | Term fees for JSS 1 A: Tuition (required), PTA levy (required), Transport (optional), WAEC (required, collected for WAEC). Add Tuition again | The duplicate is refused ¦ |  | 17 | 2026-11-24
SC-29 | Schools | Fees | Copy from the previous term, then from another class; edit an amount | Fills in one step; editable ¦ |  | 17 | 2026-11-24
SC-30 | Schools | Optional items | On a student's page tick Transport | The term fees include it; the draft invoice is rebuilt ¦ |  | 17 | 2026-11-24
SC-31 | Schools | Discounts | A 10% Sibling discount with a reason; a Scholarship larger than the fees | Discount shows as its own negative line. Nothing comes off WAEC. Total never below zero ¦ |  | 17 | 2026-11-24
SC-32 | Schools | Discounts | End a discount after an invoice was sent | Next invoices drop it; the sent one keeps it ¦ |  | 17 | 2026-11-24
SC-33 | Schools | Discount threshold | Discount threshold ₦20,000; as the Bursar add a ₦25,000 discount | Recorded as a request, shown in Approvals. Approved by Owner B, it stands. Declined with a reason, nothing changes | Second person | 17 | 2026-11-24
SC-34 | Schools | Fee changes | After invoicing, change Tuition | Drafts rebuilt. A sent invoice changes only by an amendment with a reason ¦ |  | 17 | 2026-11-24
SC-35 | Schools | Invoice the term | Current term's Invoices > Invoice the term; read the plan | Counts and totals by class, money collected for others, already invoiced, and who is left out and why. Nothing made yet ¦ |  | 17 | 2026-11-24 | R
SC-36 | Schools | Invoice the term | Keep them as drafts; check; Send the drafts | Guardians get an SMS and an email with a family page link | SMS, email | 17 | 2026-11-24 | R
SC-37 | Schools | Invoice the term | On another class choose Send them now | Each guardian gets SMS and email at once; earlier family credit counts first | SMS, email | 17 | 2026-11-24
SC-38 | Schools | Invoice the term | Add a new student; Invoice the term again | Only the new student is invoiced ¦ |  | 17 | 2026-11-24
SC-39 | Schools | Invoice the term | Show the plan; in another tab add a student or change a fee; then confirm | Confirmation refused: check again ¦ |  | 17 | 2026-11-24
SC-40 | Schools | Invoice content | Open one invoice and the term's invoice list | Customer is the first guardian; note has admission number, class and term but no name; due date is the fees-due date; WAEC reads "Collected on behalf of WAEC"; list filters by class and status ¦ |  | 17 | 2026-11-24
SC-41 | Schools | Invoice the term | Try to invoice a term that is not current | Not possible ¦ |  | 17 | 2026-11-24
SC-42 | Schools | Account numbers: connection | Schools > Settings > Students' account numbers: pick the Paystack test connection | Only connections that can issue are listed, with plain needs and fees. Choice audited | Paystack test | 17 | 2026-11-24
SC-43 | Schools | Who gets one | Schools > Account numbers > Check who gets one | Shows already issued, this batch (max 500), who cannot be issued yet and why. Nothing issued yet | Paystack test, email | 17 | 2026-11-24
SC-44 | Schools | Issue | Press Issue and watch | Issued and not issued with reasons. A student's page shows the number with Copy, the bank and the masked name | Paystack test | 17 | 2026-11-24 | R
SC-45 | Schools | Exactly once | Check and Issue again; Issue on a student who has one | No second account; the same number answered; one batch at a time | Paystack test | 17 | 2026-11-24
SC-46 | Schools | Issue one | On a student without one, Issue the account number | Issued and shown on the family page with Copy | Paystack test, phone | 17 | 2026-11-24
SC-47 | Schools | Pay into a student's account | Pay into a student's account (Paystack test) | Lands on that student's oldest open invoice by itself; receipt issued; Overview counts it "Matched by itself" | Paystack test | 17 | 2026-11-24 | R
SC-48 | Schools | Siblings | With the sibling setting off, overpay into child 1; turn it on and overpay again | Off: extra is child 1's credit. On: extra pays the sibling's invoice | Paystack test | 17 | 2026-11-24
SC-49 | Schools | Look-back | With the Paystack webhook removed, pay into a student account and wait 15 minutes | Still found and matched. Owners told once a day the webhook may be missing. Next close lists it under "Found only by the look-back" | Paystack test | 17 | 2026-11-24
SC-50 | Schools | Post a payment | As the Bursar, Schools > Payments > Post a payment: admission number, ₦20,000, cash, a note | "₦20,000 posted… (receipt RCT-…)". Invoice shows it "Received by the school" by the Bursar today. Audited | Second person (Bursar) | 17 | 2026-11-24 | R
SC-51 | Schools | Post a payment | Post a transfer and a POS payment with a past date | Both counted; Overview's How parents paid shows each ¦ |  | 17 | 2026-11-24
SC-52 | Schools | Post a payment | Post more than all of a student's open invoices | Oldest paid first; the rest becomes family credit ¦ |  | 17 | 2026-11-24
SC-53 | Schools | Post a payment | An unknown admission number; and double-tap Post | Unknown refused; no duplicate posting | Phone | 17 | 2026-11-24
SC-54 | Schools | Cash threshold | Cash threshold ₦50,000. Post exactly ₦50,000, then ₦49,999 | The first waits for a second person; the second posts at once | Second person | 18 | 2026-11-25 | R
SC-55 | Schools | Waiting | Open the ₦50,000 request in Payments and on the invoice | "Waiting for a second person". Not yet on the fees, money log or invoice ¦ |  | 18 | 2026-11-25
SC-56 | Schools | Four-eyes | Owner A posts ₦60,000, then tries to approve it | Cannot: "You asked for this, so a second person decides it" ¦ |  | 18 | 2026-11-25
SC-57 | Schools | Approve on Telegram | Owner B taps Approve on Telegram; then tries Approve again in the web app | Posted once with a receipt; the second decision refused; requester notified; audited | Telegram, second person | 18 | 2026-11-25 | R
SC-58 | Schools | Decline | Decline without a reason, then with one | No reason refused. With a reason: nothing posted; reason kept; requester told | Second person | 18 | 2026-11-25
SC-59 | Schools | Threshold settings | Cash threshold 0 and post ₦100; clear the threshold and post ₦1,000,000 | At 0 every posting waits; empty means no second person ¦ |  | 18 | 2026-11-25
SC-60 | Schools | Receipts | Schools > Receipts: find a receipt by its number typed in lowercase | Found. Numbers run RCT-2026T1-0001, 0002… per term. The invoice names the receipt ¦ |  | 18 | 2026-11-25
SC-61 | Schools | Receipt PDF | Open PDF on phone and computer; print or save | A5 page with ₦ correct, school, student, class, amount, date, how received, balance after, number and QR. Opening is audited | Phone | 18 | 2026-11-25 | R
SC-62 | Schools | Check receipt | Scan the QR code with a phone | Only Valid, school name, amount and date. No student or invoice | Phone | 18 | 2026-11-25 | R
SC-63 | Schools | Check receipt | Type a receipt number or a made-up code into the check address | Not found ¦ |  | 18 | 2026-11-25
SC-64 | Schools | Void | Undo a payment matched to the wrong invoice | Receipt marked Voided with why; keeps its number; QR shows Voided; next payment gets a new number ¦ |  | 18 | 2026-11-25
SC-65 | Schools | Family page | Open the link from the invoice SMS on a phone; switch children; bookmark one | This term's lines, discounts, WAEC label, paid and due, balance, family credit, account number with Copy, receipts | SMS, phone | 18 | 2026-11-25 | R
SC-66 | Schools | Family page | For a child with no account number, pay by Paystack test card | Counted; receipt appears; page updates | Paystack test, phone | 18 | 2026-11-25
SC-67 | Schools | I have paid | Submit an "I have paid" claim (₦15,000 cash) | Fees do not change. Shows in To match under "Families say they paid" | Phone | 18 | 2026-11-25
SC-68 | Schools | Claims | Post ₦15,000 cash for that student; dismiss another claim with a reason | First becomes "found and counted"; the other "dismissed"; family page shows each | Phone | 18 | 2026-11-25
SC-69 | Schools | Claims limit | Submit 6 claims within an hour | The 6th is refused | Phone | 18 | 2026-11-25
SC-70 | Schools | Payment plan request | Ask for a payment plan in 3 instalments; ask again | Reaches Payment plans; the second is refused while the first is undecided | Phone | 18 | 2026-11-25
SC-71 | Schools | Family links | Set links to last 1 day. After expiry open the old link and press Send me a new link 4 times; open a made-up link | Expired: "ask the school for a new link" and a new one sent to the guardian. 4th in an hour refused. Made-up: same words, no button | SMS, phone | 18 | 2026-11-25
SC-72 | Schools | Send a link | On Families press Send a link | Shown and sent; audited | SMS | 18 | 2026-11-25
SC-73 | Schools | Debtors | Set the fees-due date in the past; Schools > Debtors; pick an age group, filter by class, Download CSV | Totals for the 5 age groups; rows with balance, last reminder, promise and plan; CSV masked ¦ |  | 18 | 2026-11-25
SC-74 | Schools | Debtors | Part-pay one, fully pay another, withdraw one who owes | Balance lowers; paid one leaves the list; withdrawn stays with status ¦ |  | 18 | 2026-11-25
SC-75 | Schools | Reminder wording | Settings > Reminder wording: add {foo}; leave out {link}; exceed 600 characters; leave a step empty | {foo} refused; missing {link} added; over 600 refused; empty keeps default; preview shows samples ¦ |  | 18 | 2026-11-25
SC-76 | Schools | Send reminders | Select two siblings and one other student; step 1; send | One message per guardian naming both children; Telegram if linked, else SMS; school name first | SMS, Telegram | 19 | 2026-11-26
SC-77 | Schools | Send reminders | Select 51 students; then send step 1 again to the same family that day | 51 refused. The repeat skipped as "sent today". Skips show reasons ¦ |  | 19 | 2026-11-26
SC-78 | Schools | Promise to pay | Record a promise; try a second; send a reminder | One open promise only. Reminder skips the family. Past dates or over a year ahead refused ¦ |  | 19 | 2026-11-26
SC-79 | Schools | Promise kept or missed | After the date press Check promises and plans now (no payment; then after part payment); run again | No payment: missed and bursar told. Payment: kept. Running again changes nothing ¦ |  | 19 | 2026-11-26
SC-80 | Schools | Payment plans | Owner B approves a request with changed instalments; declines another with a note; the Bursar tries to decide one | Family told at once with a fresh link. The Bursar cannot decide | Telegram or SMS, second person | 19 | 2026-11-26
SC-81 | Schools | Plan standing | Grace 0; let an instalment date pass; Check now; then pay | In arrears and bursars told once; reminders resume. Paying restores good standing. Grace accepts 0 to 60 only ¦ |  | 19 | 2026-11-26
SC-82 | Schools | Clearance rule | Schools > Clearance by class | Paid in full: Cleared. Part paid: Partly paid. Unpaid or not invoiced with required fees: Not paid. No required fees: Cleared. Plan in good standing: Cleared. CSV masked ¦ |  | 19 | 2026-11-26 | R
SC-83 | Schools | Clearance live | Pay a not-paid student in full; undo the match | Flips to Cleared at once, then back ¦ |  | 19 | 2026-11-26
SC-84 | Schools | Overrides | Owner B: Clear by override without a reason, then with one; try a second; withdraw | No reason refused; end date defaults to end of term; a second refused; withdraw stops it; audited. The Bursar has no Clear by override | Second person | 19 | 2026-11-26
SC-85 | Schools | Override ends | Set an override ending today; check tomorrow | No longer counts ¦ |  | 19 | 2026-11-26
SC-86 | Schools | The gate | As the Gate user on a phone: search 2 letters then 3; tap a cleared, partly paid, overridden and withdrawn child; try light and dark mode | Needs 3 letters. "CLEARED" or "SEE THE BURSAR" in large type, never an amount. Overridden is cleared. Withdrawn not found | Phone, second person (Gate) | 19 | 2026-11-26 | R
SC-87 | Schools | The gate | Post cash for a "see the bursar" child and check again; search very fast; sign out and in | Cleared within a minute. Fast searching slowed. Just-checked list cleared on sign-out | Phone | 19 | 2026-11-26
SC-88 | Schools | The gate (bursar) | As the Bursar: Clearance > Open the gate screen | Same screen, no amounts ¦ |  | 19 | 2026-11-26
SC-89 | Schools | Overview | Schools > Overview on a phone; choose another term | Collected against expected, this week, outstanding, matched by itself against by a person, how parents paid, collected for others, ages, top 5 debtors (masked), cleared and the last close all agree with the rest of the app | Phone | 19 | 2026-11-26
SC-90 | Schools | Daily close | Overview > The daily close: Close yesterday now, then again; make a payment afterwards | Second press shows the stored close. A later payment does not change it. Says whether it reconciles; links each item; names no students ¦ |  | 19 | 2026-11-26 | R
SC-91 | Schools | Daily close | Wait for the next morning's automatic close | It appears; the proprietor is told on Telegram | Telegram | 19 | 2026-11-26
SC-92 | Schools | Summaries | With a term current, read the daily Telegram money summary and the monthly email | Each has a schools line: collected, outstanding, % cleared | Telegram, email | 19 | 2026-11-26
SC-93 | Schools | Template: account numbers | Turn on "Give each new student their own account number"; add a student | Number within 15 minutes; the family is messaged | Paystack test, SMS | 19 | 2026-11-26
SC-94 | Schools | Template: invoice the term | Turn on "Bill the term's fees when the term starts"; run it by hand | The bursar gets the counts ¦ |  | 19 | 2026-11-26
SC-95 | Schools | Template: reminders | Turn on "Remind families of school fees every week"; run it | Step chosen by days overdue; at most 50; skips promises and good-standing plans | SMS, Telegram | 19 | 2026-11-26
SC-96 | Schools | Templates: receipt, plan, close, gate list | Turn on the receipt, plan decided, daily close and gate list templates; trigger each | Receipt once per payment with check link; plan decision messaged; close flags a day that does not reconcile; gate list one message per class, no amounts | SMS, Telegram | 19 | 2026-11-26
XC-01 | Across the product | Browsers | Repeat the smoke test in Chrome, Firefox, and Safari (if you have a Mac or iPhone) and Edge | Same behaviour in each; log any layout break with the browser name |  | 15 | 2026-11-20
XC-02 | Across the product | Phone | Use the main pages on a small Android phone (5 to 6 inch) in Chrome | Nothing cut off; buttons big enough to tap; no sideways scrolling | Phone | 15 | 2026-11-20
XC-03 | Across the product | Slow network | In Chrome DevTools set the network to "Slow 3G" (or use a weak mobile signal); open a storefront and the dashboard | Pages still load; note load times; nothing hangs forever |  | 15 | 2026-11-20
XC-04 | Across the product | Offline | Turn data off mid-action (saving a row, paying) | A plain error; nothing saved twice when you retry |  | 15 | 2026-11-20
XC-05 | Across the product | Double clicks | Double-click or double-tap Save, Pay, Approve, Publish, Send | Only one action happens (one row, one payment, one message) |  | 15 | 2026-11-20 | R
XC-06 | Across the product | Back button | Use the browser Back and Refresh in the middle of forms and payments | No duplicate actions; no lost work without a warning |  | 15 | 2026-11-20
XC-07 | Across the product | Long and odd input | Enter very long names, names with apostrophes (Ọlá, O'Neil), emojis, ₦ signs, leading spaces | Saved and shown correctly, or refused with a reason; never a crash |  | 15 | 2026-11-20
XC-08 | Across the product | Amounts | Enter amounts as 25000, 25,000, 25k, 0, -500, 0.5 | Each understood or refused clearly; money is never wrong by a factor of 100 |  | 20 | 2026-11-27
XC-09 | Across the product | Dates and time | Check every date and time shown is Lagos time and in a clear format | Consistent, and correct around midnight |  | 20 | 2026-11-27
XC-10 | Across the product | Isolation | With two organisations, copy the address of a record (invoice, table, order) from one and open it signed in to the other | Not found or refused: one business never sees another's data |  | 20 | 2026-11-27 | R
XC-11 | Across the product | Plain words | On every page and every chat message, note technical words or confusing English | Logged as S4 (wording) with a suggested plain alternative |  | 20 | 2026-11-27
XC-12 | Across the product | Accessibility | Use Tab and Enter to move through sign-in, a form and a payment; zoom the browser to 200% | Everything reachable by keyboard; nothing breaks at 200% |  | 20 | 2026-11-27
XC-13 | Across the product | Errors | Note any page that shows a raw error, a code, "undefined", "null" or an endless spinner | Logged with the address and steps |  | 20 | 2026-11-27
XC-14 | Across the product | Emails and SMS | Read every email and SMS Taskiem sends during the month | Correct business name, no broken links, no technical words, sensible sender | Email, SMS | 20 | 2026-11-27

## Bugs
Bugs
One row per bug. Row 4 is an example: delete it before your first weekly report.
Bug ID | Date found | Time found | Test case | Area | Title | Steps to reproduce | Expected | Actual | Severity | Type | Device and browser | Account and organisation | Evidence link | Status | Priority | Assigned to | Fixed on | Retest date | Ever set to Needs info? | S1 messaged within 1 hour? | Working days to retest | Notes
BUG-000 (example) | 2026-11-10 | 10:42 | RC-28 | Reconciliation | Part payment of ₦4,000 leaves the invoice showing "Awaiting payment" instead of "Part-paid" | 1. QA Trading, Invoices > Settings: Customers may pay part ON. 2. New invoice ₦10,000 to Customer 1; Send. 3. On Customer 1's phone, pay ₦4,000 by card (Paystack test). 4. Wait 1 minute; refresh the invoice. | Part-paid; paid ₦4,000; due ₦6,000 | Stays "Awaiting payment"; paid ₦0. Paystack test shows the payment successful at 10:42 | S1 | Bug | Tecno Spark 10, Chrome | Customer 1; QA Trading | (link to BUG-000-1.png) | Fixed: ready to retest | P1 | (engineer) | 2026-11-11 | 2026-11-12 | No | Yes | 1 | Invented example to show the format
Formulas:
Working days to retest = IF(AND([Fixed on]<>"",[Retest date]<>""),NETWORKDAYS([Fixed on],[Retest date])-1,"")

## Daily log
Daily log
Fill in by 17:30 each day. The grey-headed count columns fill themselves from the Test cases tab (by planned day).
Day | Date | Planned cases | With a result | Pass | Fail | Blocked | Not run | Bugs logged today | S1 and S2 bug IDs | Retested | Closed | Reopened | Blockers, and who you told | Staging updates seen | Notes | Done by 17:30?
1 | 2026-11-02 | 8 | 0 | 0 | 0 | 0 | 0 | 0
2 | 2026-11-03 | 18 | 0 | 0 | 0 | 0 | 0 | 0
3 | 2026-11-04 | 17 | 0 | 0 | 0 | 0 | 0 | 0
4 | 2026-11-05 | 16 | 0 | 0 | 0 | 0 | 0 | 0
5 | 2026-11-06 | 19 | 0 | 0 | 0 | 0 | 0 | 0
6 | 2026-11-09 | 26 | 0 | 0 | 0 | 0 | 0 | 0
7 | 2026-11-10 | 26 | 0 | 0 | 0 | 0 | 0 | 0
8 | 2026-11-11 | 26 | 0 | 0 | 0 | 0 | 0 | 0
9 | 2026-11-12 | 21 | 0 | 0 | 0 | 0 | 0 | 0
10 | 2026-11-13 | 16 | 0 | 0 | 0 | 0 | 0 | 0
11 | 2026-11-16 | 19 | 0 | 0 | 0 | 0 | 0 | 0
12 | 2026-11-17 | 25 | 0 | 0 | 0 | 0 | 0 | 0
13 | 2026-11-18 | 18 | 0 | 0 | 0 | 0 | 0 | 0
14 | 2026-11-19 | 14 | 0 | 0 | 0 | 0 | 0 | 0
15 | 2026-11-20 | 7 | 0 | 0 | 0 | 0 | 0 | 0
16 | 2026-11-23 | 25 | 0 | 0 | 0 | 0 | 0 | 0
17 | 2026-11-24 | 26 | 0 | 0 | 0 | 0 | 0 | 0
18 | 2026-11-25 | 22 | 0 | 0 | 0 | 0 | 0 | 0
19 | 2026-11-26 | 23 | 0 | 0 | 0 | 0 | 0 | 0
20 | 2026-11-27 | 7 | 0 | 0 | 0 | 0 | 0 | 0

## Exploratory
Exploratory sessions
One row per session. Charters are from the plan, section 4.3.
Session | Day | Date | Charter | Minutes spent | What I tried | Bugs found (IDs) | Questions and ideas
1 | 5 | 2026-11-06 | Explore the workflow builder as a shop owner who has never used software like it, on a phone, to find where they would get stuck or lost
2 | 10 | 2026-11-13 | Explore reconciliation with a messy month of money (a bank statement with odd references, part payments, a refund) to find wrong totals, lost payments or double counting
3 | 15 | 2026-11-20 | Explore the storefront as a customer on a cheap phone and a slow network who orders, pays, changes their mind and books, to find anything that confuses or fails them
4 | 19 | 2026-11-26 | Explore resumption morning at a school: parents paying cash, the gate checking children, the proprietor reading the close, to find delays, wrong clearance or confusing screens
5 | 20 | 2026-11-27 | Free session: go back to the area with the most bugs and dig deeper

## Accounts
Test identities and organisations
Never write a password here.
Who | Role in Taskiem | Email | Phone (last 4 digits) | Organisations | Telegram linked? | Notes
Owner A (you) | Owner
Owner B | Owner
Admin | Admin
Operator | Operator
Viewer or Auditor | Viewer
Bursar | Bursar (custom role)
Gate | Gate
Customer 1 | No account
Customer 2 | No account
Customer 3 | No account
Field agent | Registered agent
Platform operator | Operator console
Organisations
Organisation | Used for | Owner | Created on | Notes
QA Trading | Core, chat, reconciliation
QA Shop | Storefront (one-person business)
QA Shop Two | Chat set-up, agent sign-up
QA School | Schools
QA School Two | Promotion
QA Other | Isolation checks (XC-10)

## Lists (hidden)
Pass | S1 | New | Bug | Core | P1 | Yes
Pass with note | S2 | Confirmed | Wording | Chat | P2 | No
Fail | S3 | Needs info | Design or usability | Reconciliation | P3
Blocked | S4 | In progress | Doc mismatch | Storefront
Not run |  | Fixed: ready to retest | Suggestion | Schools
|  | Closed |  | Across
Reopened
Won't fix
Duplicate
Not a bug